## Change Order Log
Project Number & Name | [18 empty] | 2026-08-25
CHANGE ORDER LOG | [18 empty] | *** Note to move values from COPs to associated CO once CO is EXECUTED so values are not double calculated.
CO/COP # | DESCRIPTION | STATUS | ESTIMATED COST |  |  |  | SUBMITTED COST |  |  |  | EXECUTED CHANGES |  |  |  |  | Schedule Impact In Days | Date SUBMITTED | Date APPROVED | CO# | NOTES
|  |  | CM Contingency | Buyout Savings | Contract | ODP Tax Savings | CM Contigency | Buyout Savings | Contract | ODP Tax Savings | CM Contingency | Buyout Savings | Contract | ODP Tax Savings | COPs in COs
CO 01 |  | Estimated
COP 001 |  | Submitted to PDC
COP 002 |  | Sent to A/E
COP 003 |  | CM to Revise
COP 004 |  | A/E Approved
COP 005 |  | Executed
CO 02 |  | Estimated
Estimated
Estimated
Estimated
Estimated
Estimated
Estimated
Estimated
Estimated
Estimated
Estimated
Estimated
Estimated
Estimated
Estimated
Estimated
Estimated
Estimated
Estimated
Estimated
Estimated
Estimated
Estimated
Estimated
Estimated
Estimated
Estimated
Estimated
Estimated
Estimated
Estimated
Estimated
Estimated
Estimated
Estimated
Estimated
Estimated
Estimated
Estimated
Estimated
Estimated
Estimated
Estimated
Estimated
Estimated
Estimated
Estimated
Estimated
SUBTOTALS |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  | Contract |  | Contingency |  | Buyout Savings |  | ODP Tax Savings |  | Substantial Completion Date |  |  | Final Completion Date
Original Contract Values |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 2028-01-01 |  |  | 2028-02-01
Total BALANCE With Currently Executed Changes |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 2028-01-01 |  |  | 2028-02-01
Total BALANCE If All Estimated & Submitted Costs Were Approved |  |  | 0 |  | 0 |  | 0 |  | 0
Estimated Funding Return To Client |  | 0
UPDATED AUGUST 2026
Formulas:
EXECUTED CHANGES = SUM(Q59*1.43)+[EXECUTED CHANGES, row above]
ODP Tax Savings = SUM(Q59*1.45)+[ODP Tax Savings, row above]

## SAMPLE Change Order Log
MP00000 / UF-XXXX Project Name | [18 empty] | 2026-08-25
CHANGE ORDER LOG
CO/COP # | DESCRIPTION | STATUS | ESTIMATED COST |  |  |  | SUBMITTED COST |  |  |  | EXECUTED CHANGES |  |  |  |  | SCHEDULE IMPACT IN DAYS | DATE SUBMITTED | DATE APPROVED | CO# | NOTES
|  |  | CM Contingency | Buyout Savings | Contract | ODP Tax Savings | CM Contigency | Buyout Savings | Contract | ODP Tax Savings | CM Contingency | Buyout Savings | Contract | ODP Tax Savings | COPs in COs
CO 01 |  | Executed | [9 empty] | 544203 |  |  |  | 0 | 2026-04-09 | 2026-04-09 | 1
COP 002
COP 003
COP 004 |  | Executed | [12 empty] | -149349.84 |  | 2026-04-10 | 2026-07-07 | 7
COP 005 |  | Executed | [12 empty] | -319667.57 |  | 2026-05-04 | 2026-05-19 | 4
COP 006 |  | Executed | [12 empty] | -3000 |  | 2026-05-04 | 2026-05-28 | 5
CO 02 |  | Executed | [9 empty] | 28069.27 | -461511.86 | 28069.27 |  |  | 2026-04-09 | 2026-04-10 | 2
COP 007 |  | Executed | [12 empty] | -2523.4 |  | 2026-05-04 | 2026-05-19 | 4
COP 008 |  | Executed | [12 empty] | 1801.44 |  | 2026-05-04 | 2026-05-19 | 4
COP 009 |  | Executed | [12 empty] | 785185.11 | 90 | 2026-05-22 | 2026-06-01 | 5
COP 010 |  | Executed | [12 empty] | -5425.54 |  | 2026-05-05 | 2026-06-09 | 6
COP 011 |  | Executed | [12 empty] | -5637.5 |  | 2026-05-04 | 2026-05-18 | 4
COP 012 |  | Executed | [12 empty] | -5673 |  | 2026-04-10 | 2026-04-27 | 3
COP 013 |  | Executed | [12 empty] | -29979.26 |  | 2026-04-10 | 2026-05-19 | 4
COP 014 |  | Executed | [12 empty] | -4060.18 |  | 2026-05-04 | 2026-05-19 | 4
COP 015 |  | Submitted to PDC | [5 empty] | -30047.16 | [8 empty] | 2026-05-27
COP 016 |  | Executed | [12 empty] | -27927.17 |  | 2026-05-05 | 2026-06-09 | 7
COP 017 |  | Executed | [12 empty] | -2824.51 |  | 2026-05-04 | 2026-06-09 | 6
COP 018 |  | Executed | [12 empty] | -9350 |  | 2026-05-07 | 2026-06-18 | 7
COP 019 |  | Executed | [12 empty] | -2429 |  | 2026-05-04 | 2026-05-19 | 4
COP 020 |  | Executed
COP 021 |  | Executed | [12 empty] | -2970 |  | 2026-04-15 | 2026-04-27 | 3
COP 022 |  | Executed | [12 empty] | -15500 |  | 2026-04-15 | 2026-04-27 | 3
COP 023 |  | Executed | [12 empty] | -11995 |  | 2026-04-15 | 2026-05-19 | 4
COP 024 |  | Executed | [12 empty] | -3805 |  | 2026-04-22 | 2026-05-18 | 4
CO 03 |  | Executed | [9 empty] | 232818 | -514938 |  |  |  | 2026-04-30
COP 025 |  | Executed | [9 empty] | -14125.22 |  |  |  |  | 2026-08-07 | 2026-08-18
COP 026 |  | Executed | [12 empty] | -3604.54 |  | 2026-06-18 | 2026-06-22 | 7
COP 027 |  | Executed | [12 empty] | -18462.22 |  | 2026-06-02 | 2026-06-09 | 6
COP 028 |  | Executed | [12 empty] | -51303.12 |  | 2026-04-29 | 2026-06-01 | 5
COP 029 |  | Executed | [12 empty] | -8645 |  | 2026-05-04 | 2026-05-28 | 5
CO 04 |  | Executed | [8 empty] | -4782.14 | -369230.31 | -20148.72 | 1283.92 |  |  | 2026-05-20 | 2026-05-28
CO 05 |  | Executed | [8 empty] | -75466 | 12517.88 | 785185.11 |  |  |  | 2026-06-04 | 2026-06-09
CO 06 |  | Executed | [8 empty] | -5425.54 | -25341.87 |  |  |  |  | 2026-06-11 | 2026-06-22
COP 030 |  | Executed | [12 empty] | -3745.8 |  | 2026-07-22 | 2026-07-23 | 8
COP 031 |  | Executed | [12 empty] | -17696.8 |  | 2026-06-19 | 2026-07-02 | 7
COP 032 |  | Sent to A/E | [5 empty] | -80640.1 | [8 empty] | 2026-08-11
COP 033 |  | Executed | [12 empty] | -12441.88 |  | 2026-07-02 | 2026-07-10 | 8
COP 034 |  | Executed | [12 empty] | -14102.78 |  | 2026-06-30 | 2026-07-10 | 8
CO 07 |  | Executed | [8 empty] | -9350 | -198578.35 |  |  |  |  | 2026-07-07 | 2026-07-10
COP 035 |  | Executed | [12 empty] | -3177 |  | 2026-07-10 | 2026-07-26 | 8
COP 036 |  | Executed | [12 empty] | -1056.25 |  | 2026-07-15 | 2026-07-26 | 8
COP 037 |  | Executed | [12 empty] | -33788.94 |  | 2026-07-17 | 2026-07-26 | 8
CO 08 |  | Executed | [8 empty] | -29721.66 | -32820.99 | -5750 |  |  |  | 2026-07-24 | 2026-08-06
COP 038 |  | Executed | [8 empty] | -1510.19 | [5 empty] | 2026-08-07 | 2026-08-14
COP 039 |  | Sent to A/E |  |  |  |  | -1343.39 | [9 empty] | 2026-08-14
COP 040 |  | Executed | [9 empty] | -4933.94 |  |  |  |  | 2026-08-19 | 2026-08-25
COP 41 |  | Submitted to PDC | [5 empty] | -37686.13 | [8 empty] | 2026-08-25
SUBTOTALS |  |  | 0 | 0 | 0 | 0 | -1343.39 | -148373.39 | 0 | 0 | -126255.53 | 172577.47 | -217163.47 | 29353.19 |  | 90
|  | Contract |  | Contingency |  |  | Buyout Savings |  | ODP Tax Savings |  |  | Substantial Completion Date |  |  | Final Completion Date
Original Contract Values |  | 7783815 |  | 216254 |  |  | 0 |  | 29353.19 |  |  | 2026-09-30 |  |  | 2026-10-29
Total BALANCE With Currently Executed Changes |  | 7566651.53 |  | 89998.47 |  |  | 172577.47 |  | 29353.19 |  |  | 2027-02-05 16:48 |  |  | 2027-03-08 12:00
Total BALANCE If All Estimated & Submitted Costs Were Approved |  | 7566651.53 |  | 88655.08 |  |  | 24204.08 |  | 29353.19
Estimated Funding Return To Client |  | 142212.35
Formulas:
Buyout Savings = SUM(Q59*1.43)+[Buyout Savings, row above]
COPs in COs = SUM(Q59*1.45)+[COPs in COs, row above]