## Calculator
Yellow incicates a field you can populate
Light blue indicates a locked field
Construction Duration (wks)
Max Cost of Work
CM Contingency %
CM Contingency | 0
Staffing | 0
|  |  | Construction Duration (months) | Base GC/Month
Base General Conditions | 0 |  | 0 | 0
Special General Conditions | 0 | (Heavy equip. rental, etc.)
Total General Conditions | 0
Construction Budget | 0
OH&P % |  |  | Bonds & Insurance | Permit | Pre-Con
OH&P |  |  | 0 |  | 0
Bonds, Ins, Permit, Pre-Con | 0
Guaranteed Max Price | 0
Pre-Con | Liquidated Damages/day
0 | 0
| Staffing | UF Expectations / Guidelines for Staffing and Allowance
| PM | PE | Super | Admin | Safety | Truck
Capacity Percentages
Total Hours
Weekly Cost
Total Staffing Cost

## Source Data
COW
| PM | PE | Super | Admin | Safety | Truck | Total per Week | FEE % | GC % | P&P Bond and Insurance
$0 to $500,000 | 35% | 0% | 100% | 0% | 2.5% | 100% |  | 8.1% | 4.75% | 3%
| 1443.05 | 0 | 2911.8 | 0 | 70.335 | 200 | 4425.185
| PM | PE | Super | Admin | Safety | Truck | Total per Week | FEE % | GC % | P&P Bond and Insurance
$500,001 to $1,000,000 | 50% | 0% | 100% | 10% | 5% | 100% |  | 6.88% | 3.75% | 3%
| 2061.5 | 0 | 2911.8 | 216.56 | 140.67 | 200 | 5330.53
| PM | PE | Super | Admin | Safety | Truck | Total per Week | FEE % | GC % | P&P Bond and Insurance
$1,000,001 to $1,750,000 | 75% | 0% | 100% | 20% | 5% | 100% |  | 6.34% | 3% | 3%
| 3092.25 | 0 | 2911.8 | 433.12 | 140.67 | 200 | 6577.84
| PM | PE | Super | Admin | Safety | Truck | Total per Week | FEE % | GC % | P&P Bond and Insurance
$1,750,001 to $2,500,000 | 100% | 0% | 100% | 20% | 5% | 100% |  | 5.87% | 2.75% | 3%
| 4123 | 0 | 2911.8 | 433.12 | 140.67 | 200 | 7608.59
| PM | PE | Super | Admin | Safety | Truck | Total per Week | FEE % | GC % | P&P Bond and Insurance
$2,500,001 to $3,500,000 | 100% | 25% | 100% | 20% | 5% | 100% |  | 5.6% | 2.25% | 3%
| 4123 | 482.05 | 2911.8 | 433.12 | 140.67 | 200 | 8090.64
| PM | PE | Super | Admin | Safety | Truck | Total per Week | FEE % | GC % | P&P Bond and Insurance
$3,500,001 to $4,500,000 | 100% | 35% | 100% | 40% | 10% | 100% |  | 5.4% | 2% | 3%
| 4123 | 674.87 | 2911.8 | 866.24 | 281.34 | 200 | 8857.25
| PM | PE | Super | Admin | Safety | Truck | Total per Week | FEE % | GC % | P&P Bond and Insurance
$4,500,001 to $6,000,000 | 100% | 45% | 125% | 50% | 10% | 125% |  | 5.15% | 1.65% | 3%
| 4123 | 867.69 | 3639.75 | 1082.8 | 281.34 | 250 | 9994.58
| PM | PE | Super | Admin | Safety | Truck | Total per Week | FEE % | GC % | P&P Bond and Insurance
$6,000,001 to Limit | 100% | 60% | 150% | 50% | 15% | 150% |  | 4.85% | 1.5% | 3%
| 4123 | 1156.92 | 4367.7 | 1082.8 | 422.01 | 300 | 11152.43

## Revision Notes
Revision 15 | Staffing: Assigns lump sum weekly staffing based on (a) each roles required percentage and (b) 3/4 percentile expected staffing levels. Refer to source data tab. Is a function of COW only. General Conditions: Assigns monthly GCs based on derived function [monthly GCs = 1.4099(COW)^0.5998]. Then calculates total GCs based on inputted project duration. Monthly GCs are a function of COW only. OH&P: Assigns total OH&P based on derived function [CM Fee = 0.5878*(COW)^0.8423]. Note (1) fee does not change with project duration and (2) this is a function of [COW + Total Staffing + Total GCs + CM Contingency]. OH&P: Total project OH&P is calcuated from percentages shown in "Source Data" tab. Pre-Con Fee: Is 0.75*(CM Fee) after Construction Budget >= $150K Liquidated Damages: If construction budget is less than $100K, then LD=0. If construction budget exceeds $100K, but less than 1,113,500, then LD=250. If construction budget exceeds $1,113,500, use 0.0002x-25.982 to approximate LD values. Removed reference to Exhibit F, 7, a, 4.2.1 iii due to historical confusion associated with that tool. Cell for Bonds and for Insurance combined into one cell and to be estimated as 3% of construction budget.
V3 | Corrected GMP calculation in cell C21. Prior version had added OH&P percentage rather than OH&P value.

## Tables (hidden)
CM Fee Schedule Expectations and Guidelines for GMPs
July 1, 2023 to June 30, 2024 | [5 empty] | General Conditions Fee Schedule (excluding bond/insurance/permit)
Estimated Construction Budget (COW+CMC+Staffing+GC) excluding Bonds & Insurance | Percentage Based on the Size of the Project | 0-6 mo | 7-12 mo | Pre-Con | For the Authorization to Proceed with Construction, the Liquidated Damages/day | Estimated Construction COW+CMC | Percentage Based on COW+CMC | Total General Conditions
|  | Construction | Construction
|  | OH&P | Add proportionally to OH&P* | 7.5% of CM Fee Listed Under 0-6 Month
A | B | C | D | E | F | A | B | C
Values Up To | CM Fee Percentage | CM Fee | CM Fee |  |  | Values Up To | GC Fee Percentage | GC Fee
50000 | 10% | 5000 | 0 | 0 | 0 | 50000 | 6% | 3000
60000 | 9.75% | 5850 | 0 | 0 | 0 | 60000 | 5.75% | 3450
70000 | 9.5% | 6650 | 0 | 0 | 0 | 70000 | 5.5% | 3850
80000 | 9.5% | 7600 | 0 | 0 | 0 | 80000 | 5.5% | 4400
90000 | 9.25% | 8325 | 0 | 0 | 0 | 90000 | 5.25% | 4725
100000 | 9% | 9000 | 0 | 0 | 250 | 100000 | 5% | 5000
110000 | 8.9% | 9790 | 0 | 0 | 250 | 110000 | 4.96% | 5456
120000 | 8.8% | 10560 | 0 | 0 | 250 | 120000 | 4.92% | 5904
130000 | 8.7% | 11310 | 0 | 0 | 250 | 130000 | 4.88% | 6344
140000 | 8.6% | 12040 | 0 | 0 | 250 | 140000 | 4.84% | 6776
150000 | 8.5% | 12750 | 1912.5 | 956.25 | 250 | 150000 | 4.8% | 7200
160000 | 8.4% | 13440 | 2016 | 1008 | 250 | 160000 | 4.76% | 7616
170000 | 8.3% | 14110 | 2116.5 | 1058.25 | 250 | 170000 | 4.72% | 8024
180000 | 8.2% | 14760 | 2214 | 1107 | 250 | 180000 | 4.68% | 8424
190000 | 8.1% | 15390 | 2308.5 | 1154.25 | 250 | 190000 | 4.64% | 8816
200000 | 8% | 16000 | 2400 | 1200 | 250 | 200000 | 4.6% | 9200
210000 | 7.99% | 16779 | 2516.85 | 1258.425 | 250 | 210000 | 4.56% | 9576
220000 | 7.98% | 17556 | 2633.4 | 1316.7 | 250 | 220000 | 4.52% | 9944
230000 | 7.97% | 18331 | 2749.65 | 1374.825 | 250 | 230000 | 4.48% | 10304
240000 | 7.96% | 19104 | 2865.6 | 1432.8 | 250 | 240000 | 4.44% | 10656
250000 | 7.938% | 19843.75 | 2976.5625 | 1488.2812 | 250 | 250000 | 4.4% | 11000
260000 | 7.93% | 20618 | 3092.7 | 1546.35 | 250 | 260000 | 4.36% | 11336
270000 | 7.92% | 21384 | 3207.6 | 1603.8 | 250 | 270000 | 4.32% | 11664
280000 | 7.91% | 22148 | 3322.2 | 1661.1 | 250 | 280000 | 4.28% | 11984
290000 | 7.897% | 22902.75 | 3435.4125 | 1717.7062 | 250 | 290000 | 4.24% | 12296
300000 | 7.875% | 23625 | 3543.75 | 1771.875 | 250 | 300000 | 4.2% | 12600
310000 | 7.86% | 24366 | 3654.9 | 1827.45 | 250 | 310000 | 4.16% | 12896
320000 | 7.84% | 25088 | 3763.2 | 1881.6 | 250 | 320000 | 4.12% | 13184
330000 | 7.83% | 25839 | 3875.85 | 1937.925 | 250 | 330000 | 4.08% | 13464
340000 | 7.82% | 26588 | 3988.2 | 1994.1 | 250 | 340000 | 4.04% | 13736
350000 | 7.81% | 27335 | 4100.25 | 2050.125 | 250 | 350000 | 4% | 14000
360000 | 7.7% | 27720 | 4158 | 2079 | 250 | 360000 | 3.985% | 14344.6154
370000 | 7.68% | 28416 | 4262.4 | 2131.2 | 250 | 370000 | 3.969% | 14686.154
380000 | 7.67% | 29146 | 4371.9 | 2185.95 | 250 | 380000 | 3.954% | 15024.6156
390000 | 7.66% | 29874 | 4481.1 | 2240.55 | 250 | 390000 | 3.938% | 15360.0002
400000 | 7.65% | 30600 | 4590 | 2295 | 250 | 400000 | 3.923% | 15692.308
410000 | 7.54% | 30914 | 4637.1 | 2318.55 | 250 | 410000 | 3.908% | 16021.5388
420000 | 7.52% | 31584 | 4737.6 | 2368.8 | 250 | 420000 | 3.892% | 16347.6928
430000 | 7.51% | 32293 | 4843.95 | 2421.975 | 250 | 430000 | 3.877% | 16670.7698
440000 | 7.5% | 33000 | 4950 | 2475 | 250 | 440000 | 3.862% | 16990.7698
450000 | 7.49% | 33705 | 5055.75 | 2527.875 | 250 | 450000 | 3.846% | 17307.693
460000 | 7.38% | 33948 | 5092.2 | 2546.1 | 250 | 460000 | 3.831% | 17621.5392
470000 | 7.36% | 34592 | 5188.8 | 2594.4 | 250 | 470000 | 3.815% | 17932.3086
480000 | 7.35% | 35280 | 5292 | 2646 | 250 | 480000 | 3.8% | 18240.001
490000 | 7.34% | 35966 | 5394.9 | 2697.45 | 250 | 490000 | 3.785% | 18544.6164
500000 | 7.33% | 36650 | 5497.5 | 2748.75 | 250 | 500000 | 3.769% | 18846.155
510000 | 7.22% | 36822 | 5523.3 | 2761.65 | 250 | 510000 | 3.754% | 19144.6166
520000 | 7.2% | 37440 | 5616 | 2808 | 250 | 520000 | 3.738% | 19440.0014
530000 | 7.19% | 38107 | 5716.05 | 2858.025 | 250 | 530000 | 3.723% | 19732.3092
540000 | 7.18% | 38772 | 5815.8 | 2907.9 | 250 | 540000 | 3.708% | 20021.54
550000 | 7.17% | 39435 | 5915.25 | 2957.625 | 250 | 550000 | 3.692% | 20307.694
560000 | 7.06% | 39536 | 5930.4 | 2965.2 | 250 | 560000 | 3.677% | 20590.771
570000 | 7.04% | 40128 | 6019.2 | 3009.6 | 250 | 570000 | 3.662% | 20870.7712
580000 | 7.03% | 40774 | 6116.1 | 3058.05 | 250 | 580000 | 3.646% | 21147.6944
590000 | 7.02% | 41418 | 6212.7 | 3106.35 | 250 | 590000 | 3.631% | 21421.5406
600000 | 7% | 42000 | 6300 | 3150 | 250 | 600000 | 3.615% | 21692.31
610000 | 6.992% | 42648.15 | 6397.2225 | 3198.6112 | 250 | 610000 | 3.6% | 21960.0024
620000 | 6.983% | 43294.6 | 6494.19 | 3247.095 | 250 | 620000 | 3.585% | 22224.618
630000 | 6.974% | 43939.35 | 6590.9025 | 3295.4512 | 250 | 630000 | 3.569% | 22486.1566
640000 | 6.966% | 44582.4 | 6687.36 | 3343.68 | 250 | 640000 | 3.554% | 22744.6182
650000 | 6.957% | 45223.75 | 6783.5625 | 3391.7812 | 250 | 650000 | 3.538% | 23000.003
660000 | 6.949% | 45863.4 | 6879.51 | 3439.755 | 250 | 660000 | 3.523% | 23252.3108
670000 | 6.94% | 46501.35 | 6975.2025 | 3487.6012 | 250 | 670000 | 3.508% | 23501.5418
680000 | 6.932% | 47137.6 | 7070.64 | 3535.32 | 250 | 680000 | 3.492% | 23747.6958
690000 | 6.923% | 47772.15 | 7165.8225 | 3582.9112 | 250 | 690000 | 3.477% | 23990.7728
700000 | 6.915% | 48405 | 7260.75 | 3630.375 | 250 | 700000 | 3.462% | 24230.773
710000 | 6.906% | 49036.15 | 7355.4225 | 3677.7112 | 250 | 710000 | 3.446% | 24467.6962
720000 | 6.898% | 49665.6 | 7449.84 | 3724.92 | 250 | 720000 | 3.431% | 24701.5426
730000 | 6.889% | 50293.35 | 7544.0025 | 3772.0012 | 250 | 730000 | 3.415% | 24932.312
740000 | 6.881% | 50919.4 | 7637.91 | 3818.955 | 250 | 740000 | 3.4% | 25160.0044
750000 | 6.872% | 51543.75 | 7731.5625 | 3865.7812 | 250 | 750000 | 3.385% | 25384.62
760000 | 6.864% | 52166.4 | 7824.96 | 3912.48 | 250 | 760000 | 3.369% | 25606.1586
770000 | 6.855% | 52787.35 | 7918.1025 | 3959.0512 | 250 | 770000 | 3.354% | 25824.6204
780000 | 6.847% | 53406.6 | 8010.99 | 4005.495 | 250 | 780000 | 3.338% | 26040.0052
790000 | 6.838% | 54024.15 | 8103.6225 | 4051.8112 | 250 | 790000 | 3.323% | 26252.313
800000 | 6.83% | 54640 | 8196 | 4098 | 250 | 800000 | 3.308% | 26461.544
810000 | 6.821% | 55254.15 | 8288.1225 | 4144.0612 | 250 | 810000 | 3.292% | 26667.698
820000 | 6.813% | 55866.6 | 8379.99 | 4189.995 | 250 | 820000 | 3.277% | 26870.7752
830000 | 6.804% | 56477.35 | 8471.6025 | 4235.8012 | 250 | 830000 | 3.262% | 27070.7754
840000 | 6.796% | 57086.4 | 8562.96 | 4281.48 | 250 | 840000 | 3.246% | 27267.6986
850000 | 6.787% | 57693.75 | 8654.0625 | 4327.0312 | 250 | 850000 | 3.231% | 27461.545
860000 | 6.779% | 58299.4 | 8744.91 | 4372.455 | 250 | 860000 | 3.215% | 27652.3144
870000 | 6.77% | 58903.35 | 8835.5025 | 4417.7512 | 250 | 870000 | 3.2% | 27840.007
880000 | 6.762% | 59505.6 | 8925.84 | 4462.92 | 250 | 880000 | 3.185% | 28024.6226
890000 | 6.753% | 60106.15 | 9015.9225 | 4507.9612 | 250 | 890000 | 3.169% | 28206.1612
900000 | 6.745% | 60705 | 9105.75 | 4552.875 | 250 | 900000 | 3.154% | 28384.623
910000 | 6.736% | 61302.15 | 9195.3225 | 4597.6612 | 250 | 910000 | 3.138% | 28560.0078
920000 | 6.728% | 61897.6 | 9284.64 | 4642.32 | 250 | 920000 | 3.123% | 28732.3158
930000 | 6.719% | 62491.35 | 9373.7025 | 4686.8512 | 250 | 930000 | 3.108% | 28901.5468
940000 | 6.711% | 63083.4 | 9462.51 | 4731.255 | 250 | 940000 | 3.092% | 29067.7008
950000 | 6.702% | 63673.75 | 9551.0625 | 4775.5312 | 250 | 950000 | 3.077% | 29230.778
960000 | 6.694% | 64262.4 | 9639.36 | 4819.68 | 250 | 960000 | 3.062% | 29390.7782
970000 | 6.685% | 64849.35 | 9727.4025 | 4863.7012 | 250 | 970000 | 3.046% | 29547.7016
980000 | 6.677% | 65434.6 | 9815.19 | 4907.595 | 250 | 980000 | 3.031% | 29701.548
990000 | 6.668% | 66018.15 | 9902.7225 | 4951.3612 | 250 | 990000 | 3.015% | 29852.3174
1000000 | 6.66% | 66600 | 9990 | 4995 | 250 | 1000000 | 3% | 30000.01
1010000 | 6.651% | 67180.15 | 10077.0225 | 5038.5112 | 250 | 1010000 | 2.993% | 30227.3477
1020000 | 6.643% | 67758.6 | 10163.79 | 5081.895 | 250 | 1020000 | 2.986% | 30453.2465
1030000 | 6.634% | 68335.35 | 10250.3025 | 5125.1512 | 250 | 1030000 | 2.978% | 30677.7064
1040000 | 6.626% | 68910.4 | 10336.56 | 5168.28 | 250 | 1040000 | 2.971% | 30900.7275
1050000 | 6.617% | 69483.75 | 10422.5625 | 5211.2812 | 250 | 1050000 | 2.964% | 31122.3098
1060000 | 6.609% | 70055.4 | 10508.31 | 5254.155 | 250 | 1060000 | 2.957% | 31342.4531
1070000 | 6.6% | 70625.35 | 10593.8025 | 5296.9012 | 250 | 1070000 | 2.95% | 31561.1576
1080000 | 6.592% | 71193.6 | 10679.04 | 5339.52 | 250 | 1080000 | 2.942% | 31778.4233
1090000 | 6.583% | 71760.15 | 10764.0225 | 5382.0112 | 250 | 1090000 | 2.935% | 31994.2501
1100000 | 6.575% | 72325 | 10848.75 | 5424.375 | 250 | 1100000 | 2.928% | 32208.638
1110000 | 6.566% | 72888.15 | 10933.2225 | 5466.6112 | 250 | 1110000 | 2.921% | 32421.5871
1120000 | 6.558% | 73449.6 | 11017.44 | 5508.72 | 250 | 1120000 | 2.914% | 32633.0973
1130000 | 6.549% | 74009.35 | 11101.4025 | 5550.7012 | 250 | 1130000 | 2.906% | 32843.1686
1140000 | 6.541% | 74567.4 | 11185.11 | 5592.555 | 250 | 1140000 | 2.899% | 33051.8011
1150000 | 6.532% | 75123.75 | 11268.5625 | 5634.2812 | 250 | 1150000 | 2.892% | 33258.9948
1160000 | 6.524% | 75678.4 | 11351.76 | 5675.88 | 250 | 1160000 | 2.885% | 33464.7495
1170000 | 6.515% | 76231.35 | 11434.7025 | 5717.3512 | 250 | 1170000 | 2.878% | 33669.0654
1180000 | 6.507% | 76782.6 | 11517.39 | 5758.695 | 250 | 1180000 | 2.871% | 33871.9425
1190000 | 6.498% | 77332.15 | 11599.8225 | 5799.9112 | 250 | 1190000 | 2.863% | 34073.3807
1200000 | 6.49% | 77880 | 11682 | 5841 | 250 | 1200000 | 2.856% | 34273.38
1210000 | 6.481% | 78426.15 | 11763.9225 | 5881.9612 | 250 | 1210000 | 2.849% | 34471.9405
1220000 | 6.473% | 78970.6 | 11845.59 | 5922.795 | 250 | 1220000 | 2.842% | 34669.0621
1230000 | 6.464% | 79513.35 | 11927.0025 | 5963.5012 | 250 | 1230000 | 2.835% | 34864.7448
1240000 | 6.456% | 80054.4 | 12008.16 | 6004.08 | 250 | 1240000 | 2.827% | 35058.9887
1250000 | 6.447% | 80593.75 | 12089.0625 | 6044.5312 | 250 | 1250000 | 2.82% | 35251.7938
1260000 | 6.439% | 81131.4 | 12169.71 | 6084.855 | 250 | 1260000 | 2.813% | 35443.1599
1270000 | 6.43% | 81667.35 | 12250.1025 | 6125.0512 | 250 | 1270000 | 2.806% | 35633.0872
1280000 | 6.422% | 82201.6 | 12330.24 | 6165.12 | 250 | 1280000 | 2.799% | 35821.5757
1290000 | 6.413% | 82734.15 | 12410.1225 | 6205.0612 | 250 | 1290000 | 2.791% | 36008.6253
1300000 | 6.405% | 83265 | 12489.75 | 6244.875 | 250 | 1300000 | 2.784% | 36194.236
1310000 | 6.396% | 83794.15 | 12569.1225 | 6284.5612 | 250 | 1310000 | 2.777% | 36378.4079
1320000 | 6.388% | 84321.6 | 12648.24 | 6324.12 | 275 | 1320000 | 2.77% | 36561.1409
1330000 | 6.379% | 84847.35 | 12727.1025 | 6363.5512 | 275 | 1330000 | 2.763% | 36742.435
1340000 | 6.371% | 85371.4 | 12805.71 | 6402.855 | 275 | 1340000 | 2.755% | 36922.2903
1350000 | 6.362% | 85893.75 | 12884.0625 | 6442.0312 | 275 | 1350000 | 2.748% | 37100.7068
1360000 | 6.354% | 86414.4 | 12962.16 | 6481.08 | 275 | 1360000 | 2.741% | 37277.6843
1370000 | 6.345% | 86933.35 | 13040.0025 | 6520.0012 | 275 | 1370000 | 2.734% | 37453.223
1380000 | 6.337% | 87450.6 | 13117.59 | 6558.795 | 275 | 1380000 | 2.727% | 37627.3229
1390000 | 6.328% | 87966.15 | 13194.9225 | 6597.4612 | 275 | 1390000 | 2.719% | 37799.9839
1400000 | 6.32% | 88480 | 13272 | 6636 | 275 | 1400000 | 2.712% | 37971.206
1410000 | 6.311% | 88992.15 | 13348.8225 | 6674.4112 | 275 | 1410000 | 2.705% | 38140.9893
1420000 | 6.303% | 89502.6 | 13425.39 | 6712.695 | 275 | 1420000 | 2.698% | 38309.3337
1430000 | 6.294% | 90011.35 | 13501.7025 | 6750.8512 | 275 | 1430000 | 2.691% | 38476.2392
1440000 | 6.286% | 90518.4 | 13577.76 | 6788.88 | 275 | 1440000 | 2.683% | 38641.7059
1450000 | 6.277% | 91023.75 | 13653.5625 | 6826.7812 | 300 | 1450000 | 2.676% | 38805.7338
1460000 | 6.269% | 91527.4 | 13729.11 | 6864.555 | 300 | 1460000 | 2.669% | 38968.3227
1470000 | 6.26% | 92029.35 | 13804.4025 | 6902.2012 | 300 | 1470000 | 2.662% | 39129.4728
1480000 | 6.252% | 92529.6 | 13879.44 | 6939.72 | 300 | 1480000 | 2.655% | 39289.1841
1490000 | 6.243% | 93028.15 | 13954.2225 | 6977.1112 | 300 | 1490000 | 2.647% | 39447.4565
1500000 | 6.235% | 93525 | 14028.75 | 7014.375 | 300 | 1500000 | 2.64% | 39604.29
1510000 | 6.226% | 94020.15 | 14103.0225 | 7051.5112 | 300 | 1510000 | 2.633% | 39759.6847
1520000 | 6.218% | 94513.6 | 14177.04 | 7088.52 | 300 | 1520000 | 2.626% | 39913.6405
1530000 | 6.209% | 95005.35 | 14250.8025 | 7125.4012 | 300 | 1530000 | 2.619% | 40066.1574
1540000 | 6.201% | 95495.4 | 14324.31 | 7162.155 | 300 | 1540000 | 2.612% | 40217.2355
1550000 | 6.192% | 95983.75 | 14397.5625 | 7198.7812 | 300 | 1550000 | 2.604% | 40366.8748
1560000 | 6.184% | 96470.4 | 14470.56 | 7235.28 | 300 | 1560000 | 2.597% | 40515.0751
1570000 | 6.175% | 96955.35 | 14543.3025 | 7271.6512 | 300 | 1570000 | 2.59% | 40661.8366
1580000 | 6.167% | 97438.6 | 14615.79 | 7307.895 | 325 | 1580000 | 2.583% | 40807.1593
1590000 | 6.158% | 97920.15 | 14688.0225 | 7344.0112 | 325 | 1590000 | 2.576% | 40951.0431
1600000 | 6.15% | 98400 | 14760 | 7380 | 325 | 1600000 | 2.568% | 41093.488
1610000 | 6.141% | 98878.15 | 14831.7225 | 7415.8612 | 325 | 1610000 | 2.561% | 41234.4941
1620000 | 6.133% | 99354.6 | 14903.19 | 7451.595 | 325 | 1620000 | 2.554% | 41374.0613
1630000 | 6.124% | 99829.35 | 14974.4025 | 7487.2012 | 325 | 1630000 | 2.547% | 41512.1896
1640000 | 6.116% | 100302.4 | 15045.36 | 7522.68 | 325 | 1640000 | 2.54% | 41648.8791
1650000 | 6.107% | 100773.75 | 15116.0625 | 7558.0312 | 325 | 1650000 | 2.532% | 41784.1298
1660000 | 6.099% | 101243.4 | 15186.51 | 7593.255 | 325 | 1660000 | 2.525% | 41917.9415
1670000 | 6.09% | 101711.35 | 15256.7025 | 7628.3512 | 325 | 1670000 | 2.518% | 42050.3144
1680000 | 6.082% | 102177.6 | 15326.64 | 7663.32 | 325 | 1680000 | 2.511% | 42181.2485
1690000 | 6.073% | 102642.15 | 15396.3225 | 7698.1612 | 325 | 1690000 | 2.504% | 42310.7437
1700000 | 6.065% | 103105 | 15465.75 | 7732.875 | 325 | 1700000 | 2.496% | 42438.8
1710000 | 6.056% | 103566.15 | 15534.9225 | 7767.4612 | 350 | 1710000 | 2.489% | 42565.4175
1720000 | 6.048% | 104025.6 | 15603.84 | 7801.92 | 350 | 1720000 | 2.482% | 42690.5961
1730000 | 6.039% | 104483.35 | 15672.5025 | 7836.2512 | 350 | 1730000 | 2.475% | 42814.3358
1740000 | 6.031% | 104939.4 | 15740.91 | 7870.455 | 350 | 1740000 | 2.468% | 42936.6367
1750000 | 6.022% | 105393.75 | 15809.0625 | 7904.5312 | 350 | 1750000 | 2.46% | 43057.4988
1760000 | 6.014% | 105846.4 | 15876.96 | 7938.48 | 350 | 1760000 | 2.453% | 43176.9219
1770000 | 6.005% | 106297.35 | 15944.6025 | 7972.3012 | 350 | 1770000 | 2.446% | 43294.9062
1780000 | 5.997% | 106746.6 | 16011.99 | 8005.995 | 350 | 1780000 | 2.439% | 43411.4517
1790000 | 5.988% | 107194.15 | 16079.1225 | 8039.5612 | 350 | 1790000 | 2.432% | 43526.5583
1800000 | 5.98% | 107640 | 16146 | 8073 | 350 | 1800000 | 2.424% | 43640.226
1810000 | 5.971% | 108084.15 | 16212.6225 | 8106.3112 | 350 | 1810000 | 2.417% | 43752.4549
1820000 | 5.963% | 108526.6 | 16278.99 | 8139.495 | 350 | 1820000 | 2.41% | 43863.2449
1830000 | 5.954% | 108967.35 | 16345.1025 | 8172.5512 | 350 | 1830000 | 2.403% | 43972.596
1840000 | 5.946% | 109406.4 | 16410.96 | 8205.48 | 375 | 1840000 | 2.396% | 44080.5083
1850000 | 5.937% | 109843.75 | 16476.5625 | 8238.2812 | 375 | 1850000 | 2.388% | 44186.9817
1860000 | 5.929% | 110279.4 | 16541.91 | 8270.955 | 375 | 1860000 | 2.381% | 44292.0163
1870000 | 5.92% | 110713.35 | 16607.0025 | 8303.5012 | 375 | 1870000 | 2.374% | 44395.612
1880000 | 5.912% | 111145.6 | 16671.84 | 8335.92 | 375 | 1880000 | 2.367% | 44497.7689
1890000 | 5.903% | 111576.15 | 16736.4225 | 8368.2112 | 375 | 1890000 | 2.36% | 44598.4869
1900000 | 5.895% | 112005 | 16800.75 | 8400.375 | 375 | 1900000 | 2.353% | 44697.766
1910000 | 5.886% | 112432.15 | 16864.8225 | 8432.4112 | 375 | 1910000 | 2.345% | 44795.6063
1920000 | 5.878% | 112857.6 | 16928.64 | 8464.32 | 375 | 1920000 | 2.338% | 44892.0077
1930000 | 5.869% | 113281.35 | 16992.2025 | 8496.1012 | 375 | 1930000 | 2.331% | 44986.9702
1940000 | 5.861% | 113703.4 | 17055.51 | 8527.755 | 375 | 1940000 | 2.324% | 45080.4939
1950000 | 5.852% | 114123.75 | 17118.5625 | 8559.2812 | 375 | 1950000 | 2.317% | 45172.5787
1960000 | 5.844% | 114542.4 | 17181.36 | 8590.68 | 375 | 1960000 | 2.309% | 45263.2247
1970000 | 5.835% | 114959.35 | 17243.9025 | 8621.9512 | 400 | 1970000 | 2.302% | 45352.4318
1980000 | 5.827% | 115374.6 | 17306.19 | 8653.095 | 400 | 1980000 | 2.295% | 45440.2001
1990000 | 5.818% | 115788.15 | 17368.2225 | 8684.1112 | 400 | 1990000 | 2.288% | 45526.5295
2000000 | 5.808% | 116170 | 17425.5 | 8712.75 | 400 | 2000000 | 2.281% | 45611.42
2050000 | 5.798% | 118869.25 | 17830.3875 | 8915.1937 | 400 | 2050000 | 2.273% | 46604.2223
2100000 | 5.788% | 121558.5 | 18233.775 | 9116.8875 | 425 | 2100000 | 2.266% | 47589.8304
2150000 | 5.778% | 124237.75 | 18635.6625 | 9317.8312 | 425 | 2150000 | 2.259% | 48568.2441
2200000 | 5.768% | 126907 | 19036.05 | 9518.025 | 425 | 2200000 | 2.252% | 49539.4636
2250000 | 5.758% | 129566.25 | 19434.9375 | 9717.4687 | 425 | 2250000 | 2.245% | 50503.4887
2300000 | 5.748% | 132215.5 | 19832.325 | 9916.1625 | 425 | 2300000 | 2.237% | 51460.3196
2350000 | 5.738% | 134854.75 | 20228.2125 | 10114.1062 | 450 | 2350000 | 2.23% | 52409.9561
2400000 | 5.728% | 137484 | 20622.6 | 10311.3 | 450 | 2400000 | 2.223% | 53352.3984
2450000 | 5.718% | 140103.25 | 21015.4875 | 10507.7437 | 450 | 2450000 | 2.216% | 54287.6463
2500000 | 5.708% | 142712.5 | 21406.875 | 10703.4375 | 475 | 2500000 | 2.209% | 55215.7
2550000 | 5.698% | 145311.75 | 21796.7625 | 10898.3812 | 475 | 2550000 | 2.201% | 56136.5593
2600000 | 5.688% | 147901 | 22185.15 | 11092.575 | 475 | 2600000 | 2.194% | 57050.2244
2650000 | 5.678% | 150480.25 | 22572.0375 | 11286.0187 | 500 | 2650000 | 2.187% | 57956.6951
2700000 | 5.668% | 153049.5 | 22957.425 | 11478.7125 | 500 | 2700000 | 2.18% | 58855.9716
2750000 | 5.658% | 155608.75 | 23341.3125 | 11670.6562 | 525 | 2750000 | 2.173% | 59748.0537
2800000 | 5.648% | 158158 | 23723.7 | 11861.85 | 525 | 2800000 | 2.165% | 60632.9416
2850000 | 5.638% | 160697.25 | 24104.5875 | 12052.2937 | 525 | 2850000 | 2.158% | 61510.6351
2900000 | 5.628% | 163226.5 | 24483.975 | 12241.9875 | 550 | 2900000 | 2.151% | 62381.1344
2950000 | 5.618% | 165745.75 | 24861.8625 | 12430.9312 | 550 | 2950000 | 2.144% | 63244.4393
3000000 | 5.608% | 168255 | 25238.25 | 12619.125 | 575 | 3000000 | 2.137% | 64100.55
3050000 | 5.598% | 170754.25 | 25613.1375 | 12806.5687 | 575 | 3050000 | 2.129% | 64949.4663
3100000 | 5.588% | 173243.5 | 25986.525 | 12993.2625 | 575 | 3100000 | 2.122% | 65791.1884
3150000 | 5.578% | 175722.75 | 26358.4125 | 13179.2062 | 600 | 3150000 | 2.115% | 66625.7161
3200000 | 5.568% | 178192 | 26728.8 | 13364.4 | 600 | 3200000 | 2.108% | 67453.0496
3250000 | 5.558% | 180651.25 | 27097.6875 | 13548.8437 | 625 | 3250000 | 2.101% | 68273.1887
3300000 | 5.548% | 183100.5 | 27465.075 | 13732.5375 | 625 | 3300000 | 2.094% | 69086.1336
3350000 | 5.538% | 185539.75 | 27830.9625 | 13915.4812 | 650 | 3350000 | 2.086% | 69891.8841
3400000 | 5.528% | 187969 | 28195.35 | 14097.675 | 650 | 3400000 | 2.079% | 70690.4404
3450000 | 5.518% | 190388.25 | 28558.2375 | 14279.1187 | 675 | 3450000 | 2.072% | 71481.8023
3500000 | 5.508% | 192797.5 | 28919.625 | 14459.8125 | 675 | 3500000 | 2.065% | 72265.97
3550000 | 5.498% | 195196.75 | 29279.5125 | 14639.7562 | 700 | 3550000 | 2.058% | 73042.9433
3600000 | 5.488% | 197586 | 29637.9 | 14818.95 | 700 | 3600000 | 2.05% | 73812.7224
3650000 | 5.478% | 199965.25 | 29994.7875 | 14997.3937 | 700 | 3650000 | 2.043% | 74575.3071
3700000 | 5.468% | 202334.5 | 30350.175 | 15175.0875 | 725 | 3700000 | 2.036% | 75330.6976
3750000 | 5.458% | 204693.75 | 30704.0625 | 15352.0312 | 725 | 3750000 | 2.029% | 76078.8937
3800000 | 5.448% | 207043 | 31056.45 | 15528.225 | 725 | 3800000 | 2.022% | 76819.8956
3850000 | 5.438% | 209382.25 | 31407.3375 | 15703.6687 | 750 | 3850000 | 2.014% | 77553.7031
3900000 | 5.428% | 211711.5 | 31756.725 | 15878.3625 | 750 | 3900000 | 2.007% | 78280.3164
3950000 | 5.418% | 214030.75 | 32104.6125 | 16052.3062 | 750 | 3950000 | 2% | 78999.7353
Note 1: percentages for construction values in between the values shown above will be calculated by rounding the construction value to the nearest $10K value and using the OH&P for that category; e.g. percentage for $104,000 COW is 9% and percentage for $106,000 COW is 8.9%. | [5 empty] | The above values includes but is not limited to mobilization, transportation and storage, small office trailer, supplies, small tools/storage, first aid, safety tools & signs, background check, identification badges, camera, water/cooler, project sign, trash removal (Dumpsters), project fencing and wrap, document reproductions, cell phones, radios, postage, office material, any home office cost, portable toilets, furniture, all software, all computer/tablet services, all software licenses, all shop drawing and RFI costs, record documents, redline as-builts, aerials (drone), General/Daily Cleaning, handy man, parking, tree and utility protection, all taxes for above are included. No other creative names for any of the above listed items.
* If project duration exceed 6 months, the CM is allowed to include additional percentage proportionally for the number of weeks exceeding the 6 months shown in Column D; e.g., If three weeks extra for a $3.7M project, then ($30,350/26*3) or $3,502 will be added to the GMP for this extension.
The Liquidated Damages will be added to every Authorization to proceed on projects $100K and greater
The above lump sum values excluded the items below. The items below will be processed as actual expenditures w/backup documentation required.
[6 empty] | Bond | Insurances | Permit Fees
[6 empty] | Heavy Equipment Rental | Scaffolding Rental | Surveys/Tests
[6 empty] | Material Testing | Final Cleaning | MOT/Flagmen (see notes below)
[6 empty] | Preconstruction Services Fee | New Building Utilites (if required) | Swing Space Rental
Per Diem and travel costs will not be accepted for minor projects.
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Staffing | UF Expectations / Guidelines for Staffing and Allowance
Clarification: The staffing $$ range below is based on "Cost of Work" plus "CM Contingency" values only. | [6 empty] | Column1 | PM Quantity | PM Capacity | Sr. PM Quantity | Sr. PM Capacity | Super Quantity | Super Capacity | Sr. Super Quantity | Sr. Super Capacity | PE Quantity | PE Capacity | Admin Capacity | Safety Hrs/Week | Total Allowable Vehicle Costs/Month
Projects between $50k – 100K | One PM at 25% (or Sr. PM at 20%) Capacity. One Super at 100% Capacity (or Sr. Super at 100% Capacity but only 80% billable). Safety 1 hr. per week. Total allowable vehicle costs (vehicle, maintenance/fuel, etc.) per project is limited up to $800/month for superintendents only with back up documentation (vehicle costs only billed if not included in labor burden). |  |  |  |  | Projects between $50k – 100K | 50000 | 1 | 25% | 1 | 20% | 1 | 100% | 1 | 80% | 0 | 0% | 0% | 1 | 800
Projects between $100k – 350K | One PM at 33% (or Sr. PM at 25%) Capacity. One Super at 100% (or Sr. Super at 100% Capacity but only 80% billable). Admin personnel at 10% capacity. Safety 2 hrs. per week. Total allowable vehicle costs (vehicle, maintenance/fuel, etc.) per project is limited up to $800/month for superintendents only with back up documentation (vehicle costs only billed if not included in labor burden). |  |  |  |  | Projects between $100k – 350K | 100000 | 1 | 33% | 1 | 25% | 1 | 100% | 1 | 80% | 0 | 0% | 10% | 2 | 800
Projects between $350K - 1.0M | One PM at 50% (or Sr. PM at 40%) Capacity. One Super at 100% (or Sr. Super at 100% Capacity but only 80% billable). Admin personnel at 20% capacity. Safety 2 hrs. per week. Total allowable vehicle costs (vehicle, maintenance/fuel, etc.) per project is limited up to $800/month for superintendents only with back up documentation (vehicle costs only billed if not included in labor burden). |  |  |  |  | Projects between $350K - 1.0M | 350000 | 1 | 50% | 1 | 40% | 1 | 100% | 1 | 80% | 0 | 0% | 20% | 2 | 800
Projects between $1.0M - 1.5M | One PM at 50% (or Sr. PM at 40%) Capacity. One Super at 100% (or Sr. Super at 100% Capacity but only 80% billable). One PE at 25% Capacity. Admin personnel at 20% Capacity. Safety 2 hrs. per week. Total allowable vehicle costs (vehicle, maintenance/fuel, etc.) per project is limited up to $800/month for superintendents only with back up documentation (vehicle costs only billed if not included in labor burden). |  |  |  |  | Projects between $1.0M - 1.5M | 1000000 | 1 | 50% | 1 | 40% | 1 | 100% | 1 | 80% | 1 | 25% | 20% | 2 | 800
Projects between $1.5M - 2.0M | One PM at 75% (or Sr. PM at 60%) Capacity. One Super at 100% (or Sr. Super at 100% Capacity but only 80% billable). One PE at 25% Capacity. Admin personnel at 20% Capacity. Safety 2 hrs. per week. Total allowable vehicle costs (vehicle, maintenance/fuel, etc.) per project is limited up to $800/month for superintendents only with back up documentation (vehicle costs only billed if not included in labor burden). |  |  |  |  | Projects between $1.5M - 2.0M | 1500000 | 1 | 75% | 1 | 60% | 1 | 100% | 1 | 80% | 1 | 25% | 20% | 2 | 800
Projects between $2.0M - 3.0M | One PM at 100% (or Sr. PM at 80%) Capacity. One Super at 100% (or Sr. Super at 100% Capacity but only 80% billable). Admin personnel at 20% Capacity. Safety 2 hrs. per week. Total allowable vehicle costs (vehicle, maintenance/fuel, etc.) per project is limited up to $800/month for superintendents only with back up documentation (vehicle costs only billed if not included in labor burden). |  |  |  |  | Projects between $2.0M - 3.0M | 2000000 | 1 | 100% | 1 | 80% | 1 | 100% | 1 | 80% | 0 | 0% | 20% | 2 | 800
Projects Greater than $3.0M | One PM at 100% (or Sr. PM at 80%) Capacity. One Super at 100% (or Sr. Super at 100% Capacity but only 80% billable). One PE at 25% Capacity. Admin personnel at 20% Capacity. Safety 2 hrs. per week. Total allowable vehicle costs (vehicle, maintenance/fuel, etc.) per project is limited up to $800/month for superintendents only with back up documentation (vehicle costs only billed if not included in labor burden). |  |  |  |  | Projects Greater than $3.0M | 3000000 | 1 | 100% | 1 | 80% | 1 | 100% | 1 | 80% | 1 | 25% | 20% | 2 | 800
Note: For projects with PM and PE staffing capacity, the staffing capacity percentage for only the PE can be increased by reducing the staffing capacity percentage allocated to the PM so long as the total staffing capacity of both does not exceed the combined original staffing percentages of the PM and PE. i.e. Projects $1.0M-$1.5M, Original PM 50% PE 25% (Total combined 75%) - Modified PM 40% and PE 35% (Total combined 75%).